## Proposed Risk Analysis
Proposed Risk Analysis table
# | Risk Event | Probability / 100 | Impact, weeks | Score | Effect | Risk Mitigation Plan | Person Responsible
1 | Incorrect PV Panel Parameters in Simulation | 40 | 2 | 80 | Produces inaccurate power results, misleading performance comparison | Verify panel datasheet values before simulation, cross-check with manufacturer data | Mohammad
2 | MPPT Algorithm Fails to Converge | 30 | 3 | 90 | System cannot reach maximum power point, low efficiency | Debug step by step, test with fixed irradiance levels first | Mohammad
3 | DC-DC Converter Model Unstable | 25 | 2 | 50 | Output voltage/current fluctuates, affecting tracking | Tune converter parameters, run separate simulations to ensure stability | Meshari
4 | Sensor Model Calibration Error | 20 | 1 | 20 | Wrong data fed to algorithm, reducing accuracy | Calibrate sensors and compare against reference values | Meshari
Total risk : |  |  |  | 240
data is only a part of the full list and is included as initial consideration