## Sheet1
Period | Action | Person responsible
14-Sept-2026 till 28-Sept-2026 | Reviewing the Aim and Objectives Defining the work plan of the remaining part of the project | Faisal
29-Sept-2026 till 5-Oct-2026 | Reviewing the State of the Art part | Faisal
6-Oct-2026 till 15-Oct-2026 | Defining the algorithm of Variable Step-Size Perturb and Observe (VSS-P&O) | Faisal
16-Oct-2026 till 25-Oct-2026 | Implementing VSS-P&O on Arduino and Proteus | Faisal
26-Oct-2026 till 8-Nov-2026 | Applying the different scenarios + measurements | Faisal
8-Nov-2026 till 16-Nov-2026 | Comparison between the results of VSS-P&O and the four previous controllers on Matlab | Faisal
16-Nov-2026 till 22-Nov-2026 | Update chapters 1 and 2 and write chapter 3 | Faisal
23-Nov-2026 till 30-Nov-2026 | Write the results and the analysis chapters | Faisal
1-Dec-2026 till 10-Dec-2026 | Finalize the report | Faisal
11-Dec-2026 till 15-Dec-2026 | Prepare the presentation and all required documentation | Faisal